## Slide 1: Solina

## Slide 2: Solina: TCA technical assistance activities
# | Activity | Expected result | Duration | Value ($) | State* | Observations
1 | Strengthening leadership and management capacity building; staff performance system; introduction of new vaccines and campaigns | National EPI team with strengthened capacity and leadership skills to effectively coordinate the program | 2024-25 | $233,907 | in progress | Supported the onboarding of the EPI Director and other newly appointed EPI officials in May, 2024 Finalized plan to build capacity of 23 EPI officials Supported the country to plan, conduct and supervise the acceleration week, reaching 84% of target population (48,658) as at March 29, 2024 Supported the country to plan and conduct the Measles Rubella campaign, reaching 87% of target population (881,808) as at December 9, 2024
2 | TA for the financing of the IPE and the reinforcement of financial management, incl. the requisition of funds, mobile money disbursements and justification at SAB level | Improving government prioritization and financing of PPE, and strengthening financial accountability and transparency | 2024-25 | $107,198 | in progress | Supported administrators in FACE development and submission. Notably, 94% (15/16) of submitted FACEs were approved and disbursed between February and May, 2024 Deployed a financial accountability and monitoring tool to streamline financial management processes Supported the recruitment process to setup the Gavi management cell
3 | Support for the coordination of the EPI in SAB, Oio and Cacheu (Triple V strategy) | Effective coordination and collaboration between the regional EPI team and partners | 2024-25 | $268,111 | in progress | Finalized plan to build capacity of 23 SAB officials Conducted 80% (4/5) planned mentoring sessions across 15 HFs in SAB to build HWs Supported SAB to conduct the first ever LQAS survey in the country to assess program performance
* Implementation status: Planned; in progress; completed; delayed; canceled

## Slide 3: Solina: Technical assistance activities - Other
# | Activity | Expected result | Duration | Value ($) | State* | Observations
4 | Support to the National Programmes Team to develop existing systems and optimize the COVID data management system, facilitating the design and operations of new modalities needed to improve data quality in Guinea-Bissau. |  | 2023-24 | $165,631 | completed | Conducted a comprehensive diagnostic of the data landscape and shared findings with stakeholders Developed a Data quality improvement framework to pave the way for the development of a robust data quality improvement plan for the country Conducted a full EIR needs assessment and developed a detailed budget and report to guide the country in transitioning to the use of EIR
* Implementation status: Planned; in progress; completed; delayed; canceled

## Slide 4: Human resources funded by Gavi
# | Activity | Human resources funded by Gavi | State * | Observations
1 | Leadership and the development of management skills | Number of staff : 1 Designation: Management partner | Active | 
2 | Financing EPI and strengthening financial management | Number of staff : 1 Designation: Financial management Associate | Active | 
3 | Supporting the coordination of the EPI in SAB, Oio and Cacheu | Number of staff : 2 Designation: SAB Program Associate, Cacheu and Oio Program Associate | Active | 
4 | Supporting the National Programmes Team to develop existing systems and optimize the COVID data management system | Number of staff : 1 Designation: Data management Associate | Finished | 
* Recruitment status: planned; recruitment in progress; recruited; active; finished
In addition to the in-country staff in Guinea Bissau, there are 4 team members who also support the project from Headquarters in Nigeria